## Equipment Data
tool_id | tool_name | tool_model | tool_type | site | region | oem_vendor | program | phase | priority | status | install_status | budget | actual | variance | install_date | qual_date | ais_date | utilization | lead_time_weeks | deploy_pct | risk | asset_class | useful_life_yr | ais_status
EQP-100001 | Etch System | Lam Flex | Etch System | Bangalore | APAC | Tokyo Electron | NPI Beta | EVT | P3 | AIS Capitalized | AIS Capitalized | 1850000 | 1734167 | -115833 | Jan 2025 | Feb 2025 | Apr 2025 | 56.6 | 11 | 91 | Low | Test Equipment | 7 | Capitalized
EQP-100002 | Automated Assembly | ASE SSW | Automated Assembly | Shanghai | APAC | Advantest | Tech Refresh | DVT | P3 | Operational | Operational | 415000 | 444781 | 29781 | Aug 2025 | Sep 2025 | Nov 2025 | 52.8 | 31 | 33 | Medium | Mfg Equipment | 5 | Capitalized
EQP-100003 | Wafer Handling Robotics | Brooks Reliance | Wafer Handling Robotics | Penang | APAC | Hitachi High-Tech | Tech Refresh | DVT | P3 | Delayed | Delayed | 1620000 | 1664137 | 44137 | TBD | TBD | TBD | 59.7 | 33 | 93 | High | Test Equipment | 5 | Not Started
EQP-100004 | Etch System | Lam Flex | Etch System | Shanghai | APAC | ASM International | NPI Alpha | EVT | P4 | Installed | Installed | 1450000 | 1414612 | -35388 | Jul 2025 | TBD | TBD | 62.8 | 27 | 29 | Medium | Test Equipment | 7 | Not Started
EQP-100005 | Automated Assembly | Besi Esec | Automated Assembly | Shanghai | APAC | KLA Corporation | Automation Upgrade | DVT | P2 | AIS Capitalized | AIS Capitalized | 1850000 | 1783257 | -66743 | Jan 2025 | Mar 2025 | Apr 2025 | 85.3 | 35 | 54 | Medium | Mfg Equipment | 5 | Capitalized
EQP-100006 | Lithography System | Nikon NSR | Lithography System | Penang | APAC | Tokyo Electron | Automation Upgrade | DVT | P4 | Operational | Operational | 1620000 | 1536690 | -83310 | Oct 2025 | Dec 2025 | Feb 2026 | 82.4 | 37 | 94 | High | Tooling | 7 | Capitalized
EQP-100007 | Inspection System | KLA Puma | Inspection System | Phoenix, AZ | Americas | Advantest | NPI Alpha | EVT | P4 | PO Issued | PO Issued | 820000 | 857301 | 37301 | TBD | TBD | TBD | 64.2 | 39 | 87 | High | Automation | 5 | Not Started
EQP-100008 | Automated Assembly | Kulicke & Soffa DB | Automated Assembly | Austin, TX | Americas | ASM International | Capacity Expansion | EVT | P2 | Delayed | Delayed | 820000 | 828810 | 8810 | TBD | TBD | TBD | 70.4 | 16 | 100 | High | Automation | 5 | Not Started
EQP-100009 | Automated Assembly | Besi Esec | Automated Assembly | Shanghai | APAC | KLA Corporation | Capacity Expansion | EVT | P2 | Qualified | Qualified | 1850000 | 2041842 | 191842 | Sep 2025 | Oct 2025 | TBD | 91.5 | 29 | 50 | Medium | Mfg Equipment | 5 | In Progress
EQP-100010 | Lithography System | Nikon NSR | Lithography System | Austin, TX | Americas | Lam Research | Automation Upgrade | EVT | P4 | Operational | Operational | 1850000 | 1985358 | 135358 | Sep 2025 | Nov 2025 | Dec 2025 | 58.3 | 37 | 47 | High | Test Equipment | 7 | Capitalized
EQP-100011 | CMP Tool | Ebara F-REX | CMP Tool | Penang | APAC | Advantest | Tech Refresh | DVT | P1 | Operational | Operational | 980000 | 914149 | -65851 | Oct 2025 | Nov 2025 | Jan 2026 | 56 | 14 | 100 | Low | Mfg Equipment | 5 | Capitalized
EQP-100012 | Lithography System | TEL Lithius | Lithography System | Santa Clara, CA | Americas | Hitachi High-Tech | NPI Alpha | PVT | P2 | Operational | Operational | 1620000 | 1559812 | -60188 | Oct 2025 | Dec 2025 | Feb 2026 | 57.1 | 40 | 72 | High | Test Equipment | 7 | Capitalized
EQP-100013 | Etch System | Lam Flex | Etch System | Ho Chi Minh City | APAC | Hitachi High-Tech | Automation Upgrade | DVT | P2 | Delayed | Delayed | 415000 | 437689 | 22689 | TBD | TBD | TBD | 81.4 | 16 | 51 | High | Test Equipment | 7 | Not Started
EQP-100014 | Lithography System | Nikon NSR | Lithography System | Hsinchu, Taiwan | APAC | KLA Corporation | Automation Upgrade | EVT | P2 | Operational | Operational | 980000 | 1072999 | 92999 | Oct 2025 | Nov 2025 | Dec 2025 | 77.6 | 10 | 31 | Medium | Test Equipment | 7 | Capitalized
EQP-100015 | Metrology Tool | KLA Zeta | Metrology Tool | Hsinchu, Taiwan | APAC | Advantest | NPI Beta | DVT | P4 | Delayed | Delayed | 820000 | 816551 | -3449 | TBD | TBD | TBD | 66.2 | 41 | 39 | High | Test Equipment | 5 | Not Started
EQP-100016 | CMP Tool | AMAT Reflexion | CMP Tool | Santa Clara, CA | Americas | Applied Materials | Capacity Expansion | EVT | P1 | Demand Identified | Demand Identified | 1620000 | 1653323 | 33323 | TBD | TBD | TBD | 49 | 21 | 2 | High | Mfg Equipment | 5 | Not Started
EQP-100017 | Lithography System | ASML PAS | Lithography System | Austin, TX | Americas | Tokyo Electron | Tech Refresh | PVT | P1 | Qualified | Qualified | 650000 | 652499 | 2499 | Sep 2025 | Nov 2025 | TBD | 55.2 | 30 | 50 | Medium | Automation | 7 | In Progress
EQP-100018 | Wafer Handling Robotics | Brooks Reliance | Wafer Handling Robotics | Bangalore | APAC | Advantest | Capacity Expansion | EVT | P1 | Delayed | Delayed | 2100000 | 2351350 | 251350 | TBD | TBD | TBD | 70.3 | 18 | 64 | High | Mfg Equipment | 5 | Not Started
EQP-100019 | Lithography System | ASML PAS | Lithography System | Bangalore | APAC | KLA Corporation | Automation Upgrade | PVT | P3 | PO Issued | PO Issued | 2100000 | 2345218 | 245218 | TBD | TBD | TBD | 60 | 16 | 37 | Medium | Automation | 7 | Not Started
EQP-100020 | Etch System | Lam Flex | Etch System | Singapore | APAC | KLA Corporation | Capacity Expansion | DVT | P3 | Installed | Installed | 1280000 | 1229720 | -50280 | May 2025 | TBD | TBD | 57.6 | 13 | 31 | Medium | Tooling | 7 | Not Started
EQP-100021 | CMP Tool | AMAT Reflexion | CMP Tool | Santa Clara, CA | Americas | Hitachi High-Tech | NPI Beta | PVT | P4 | Qualified | Qualified | 820000 | 875961 | 55961 | Aug 2025 | Oct 2025 | TBD | 50.6 | 19 | 89 | Low | Mfg Equipment | 5 | In Progress
EQP-100022 | Inspection System | Hitachi SEM | Inspection System | Singapore | APAC | KLA Corporation | Automation Upgrade | EVT | P1 | PO Issued | PO Issued | 1280000 | 1407739 | 127739 | TBD | TBD | TBD | 79.1 | 16 | 65 | Low | Tooling | 5 | Not Started
EQP-100023 | Test & Calibration | Xcerra Diamond | Test & Calibration | Phoenix, AZ | Americas | Tokyo Electron | NPI Beta | EVT | P4 | Delayed | Delayed | 415000 | 396686 | -18314 | TBD | TBD | TBD | 53 | 16 | 68 | High | Mfg Equipment | 5 | Not Started
EQP-100024 | Vacuum System | Edwards STP | Vacuum System | Shanghai | APAC | Advantest | Capacity Expansion | DVT | P3 | Installed | Installed | 980000 | 945293 | -34707 | Jul 2025 | TBD | TBD | 88.2 | 27 | 64 | Medium | Tooling | 5 | Not Started
EQP-100025 | Automated Assembly | ASE SSW | Automated Assembly | Santa Clara, CA | Americas | Lam Research | Capacity Expansion | EVT | P3 | Qualified | Qualified | 1100000 | 1020416 | -79584 | Jun 2025 | Aug 2025 | TBD | 75.3 | 42 | 34 | High | Tooling | 5 | In Progress
EQP-100026 | Test & Calibration | Teradyne UltraFLEX | Test & Calibration | Bangalore | APAC | Applied Materials | Automation Upgrade | EVT | P2 | Delayed | Delayed | 1850000 | 1956137 | 106137 | TBD | TBD | TBD | 66.6 | 31 | 99 | High | Automation | 5 | Not Started
EQP-100027 | Etch System | AMAT Centris | Etch System | Bangalore | APAC | ASM International | Automation Upgrade | DVT | P2 | Operational | Operational | 1100000 | 1133970 | 33970 | Dec 2025 | Feb 2026 | Mar 2026 | 75.8 | 29 | 71 | Medium | Mfg Equipment | 7 | Capitalized
EQP-100028 | CMP Tool | Ebara F-REX | CMP Tool | Shanghai | APAC | Teradyne | Tech Refresh | PVT | P3 | Installed | Installed | 1620000 | 1633538 | 13538 | Sep 2025 | TBD | TBD | 77.9 | 28 | 85 | Medium | Automation | 5 | Not Started
EQP-100029 | Etch System | Lam Flex | Etch System | Bangalore | APAC | Tokyo Electron | NPI Beta | EVT | P1 | Installed | Installed | 980000 | 1094451 | 114451 | Feb 2025 | TBD | TBD | 89.3 | 22 | 69 | Low | Tooling | 7 | Not Started
EQP-100030 | Wafer Handling Robotics | Brooks Reliance | Wafer Handling Robotics | Phoenix, AZ | Americas | Applied Materials | NPI Alpha | DVT | P2 | Qualified | Qualified | 1850000 | 1873883 | 23883 | Mar 2025 | May 2025 | TBD | 85.1 | 30 | 76 | Medium | Tooling | 5 | In Progress
EQP-100031 | Automated Assembly | ASE SSW | Automated Assembly | Phoenix, AZ | Americas | Advantest | Automation Upgrade | DVT | P3 | Qualified | Qualified | 1100000 | 1180479 | 80479 | Nov 2025 | Jan 2026 | TBD | 67 | 28 | 50 | Medium | Automation | 5 | In Progress
EQP-100032 | Inspection System | KLA Archer | Inspection System | Singapore | APAC | Lam Research | NPI Beta | EVT | P2 | Operational | Operational | 820000 | 870252 | 50252 | Jul 2025 | Sep 2025 | Nov 2025 | 68.3 | 13 | 46 | Medium | Tooling | 5 | Capitalized
EQP-100033 | Wafer Handling Robotics | RORZE RX | Wafer Handling Robotics | Santa Clara, CA | Americas | Teradyne | Automation Upgrade | EVT | P4 | Demand Identified | Demand Identified | 1100000 | 1177764 | 77764 | TBD | TBD | TBD | 85 | 24 | 15 | Medium | Test Equipment | 5 | Not Started
EQP-100034 | CMP Tool | Ebara F-REX | CMP Tool | Hsinchu, Taiwan | APAC | Applied Materials | Automation Upgrade | DVT | P3 | PO Issued | PO Issued | 1450000 | 1544012 | 94012 | TBD | TBD | TBD | 46.3 | 35 | 95 | Medium | Mfg Equipment | 5 | Not Started
EQP-100035 | Etch System | AMAT Centris | Etch System | Ho Chi Minh City | APAC | KLA Corporation | Automation Upgrade | EVT | P1 | AIS Capitalized | AIS Capitalized | 1450000 | 1428932 | -21068 | Jun 2025 | Aug 2025 | Oct 2025 | 82.6 | 36 | 52 | High | Mfg Equipment | 7 | Capitalized
EQP-100036 | Vacuum System | Edwards STP | Vacuum System | Singapore | APAC | Applied Materials | Capacity Expansion | EVT | P3 | Delayed | Delayed | 415000 | 444401 | 29401 | TBD | TBD | TBD | 52.6 | 18 | 80 | High | Mfg Equipment | 5 | Not Started
EQP-100037 | Test & Calibration | Teradyne UltraFLEX | Test & Calibration | Hsinchu, Taiwan | APAC | ASM International | Capacity Expansion | EVT | P3 | Operational | Operational | 650000 | 699112 | 49112 | Jun 2025 | Jul 2025 | Sep 2025 | 46.3 | 29 | 93 | Medium | Tooling | 5 | Capitalized
EQP-100038 | Wafer Handling Robotics | RORZE RX | Wafer Handling Robotics | Shanghai | APAC | Lam Research | Tech Refresh | PVT | P3 | OEM Build | OEM Build | 980000 | 921572 | -58428 | TBD | TBD | TBD | 84.8 | 12 | 64 | Medium | Tooling | 5 | Not Started
EQP-100039 | Inspection System | KLA Puma | Inspection System | Singapore | APAC | Hitachi High-Tech | NPI Alpha | DVT | P3 | AIS Capitalized | AIS Capitalized | 650000 | 654358 | 4358 | Aug 2025 | Oct 2025 | Nov 2025 | 53.8 | 27 | 98 | Medium | Tooling | 5 | Capitalized
EQP-100040 | Vacuum System | Pfeiffer HiPace | Vacuum System | Guadalajara, MX | Americas | ASM International | Capacity Expansion | EVT | P3 | AIS Capitalized | AIS Capitalized | 650000 | 634260 | -15740 | Aug 2025 | Nov 2025 | Dec 2025 | 78.4 | 31 | 23 | Medium | Tooling | 5 | Capitalized
EQP-100041 | Inspection System | KLA Puma | Inspection System | Hsinchu, Taiwan | APAC | Tokyo Electron | Capacity Expansion | DVT | P2 | Operational | Operational | 2100000 | 2226497 | 126497 | Jan 2025 | Mar 2025 | Apr 2025 | 49.3 | 36 | 82 | High | Test Equipment | 5 | Capitalized
EQP-100042 | Vacuum System | Leybold MAG | Vacuum System | Hsinchu, Taiwan | APAC | Advantest | NPI Alpha | EVT | P2 | AIS Capitalized | AIS Capitalized | 1450000 | 1534618 | 84618 | Oct 2025 | Dec 2025 | Feb 2026 | 72.7 | 32 | 74 | Medium | Automation | 5 | Capitalized
EQP-100043 | Inspection System | Hitachi SEM | Inspection System | Hsinchu, Taiwan | APAC | ASM International | Capacity Expansion | DVT | P2 | OEM Build | OEM Build | 980000 | 963447 | -16553 | TBD | TBD | TBD | 55.8 | 40 | 55 | High | Automation | 5 | Not Started
EQP-100044 | Etch System | Lam Flex | Etch System | Bangalore | APAC | Tokyo Electron | Capacity Expansion | EVT | P2 | Operational | Operational | 1850000 | 1748835 | -101165 | Jan 2025 | Apr 2025 | May 2025 | 79.9 | 18 | 82 | Low | Mfg Equipment | 7 | Capitalized
EQP-100045 | PECVD System | TEL Trias | PECVD System | Bangalore | APAC | Advantest | Automation Upgrade | DVT | P2 | Demand Identified | Demand Identified | 415000 | 402755 | -12245 | TBD | TBD | TBD | 69.6 | 13 | 4 | Medium | Test Equipment | 7 | Not Started
EQP-100046 | Test & Calibration | Advantest T2000 | Test & Calibration | Austin, TX | Americas | Tokyo Electron | NPI Alpha | PVT | P3 | Installed | Installed | 2100000 | 2182373 | 82373 | Sep 2025 | TBD | TBD | 90.4 | 29 | 95 | Medium | Tooling | 5 | Not Started
EQP-100047 | CMP Tool | Lam Sabre | CMP Tool | Guadalajara, MX | Americas | Applied Materials | Tech Refresh | PVT | P1 | Operational | Operational | 980000 | 1024200 | 44200 | Feb 2025 | Apr 2025 | May 2025 | 53.7 | 14 | 40 | High | Mfg Equipment | 5 | Capitalized
EQP-100048 | Wafer Handling Robotics | Entegris Probot | Wafer Handling Robotics | Guadalajara, MX | Americas | Advantest | Capacity Expansion | EVT | P2 | AIS Capitalized | AIS Capitalized | 1100000 | 1166657 | 66657 | Dec 2025 | Feb 2026 | Mar 2026 | 84.4 | 22 | 74 | Low | Mfg Equipment | 5 | Capitalized
EQP-100049 | Automated Assembly | Kulicke & Soffa DB | Automated Assembly | Phoenix, AZ | Americas | ASM International | NPI Beta | EVT | P1 | PO Issued | PO Issued | 1100000 | 1142909 | 42909 | TBD | TBD | TBD | 68.4 | 29 | 71 | Medium | Automation | 5 | Not Started
EQP-100050 | Automated Assembly | Besi Esec | Automated Assembly | Hsinchu, Taiwan | APAC | Advantest | NPI Alpha | PVT | P1 | Installed | Installed | 1450000 | 1547014 | 97014 | Jan 2025 | TBD | TBD | 93.1 | 11 | 54 | Medium | Mfg Equipment | 5 | Not Started
EQP-100051 | Metrology Tool | KLA Zeta | Metrology Tool | Singapore | APAC | Advantest | Capacity Expansion | EVT | P4 | AIS Capitalized | AIS Capitalized | 1450000 | 1518087 | 68087 | Feb 2025 | Apr 2025 | Jun 2025 | 65.4 | 30 | 33 | Medium | Test Equipment | 5 | Capitalized
EQP-100052 | Inspection System | KLA Archer | Inspection System | Hsinchu, Taiwan | APAC | ASM International | Automation Upgrade | PVT | P1 | AIS Capitalized | AIS Capitalized | 650000 | 638887 | -11113 | Jul 2025 | Oct 2025 | Nov 2025 | 77.9 | 39 | 72 | High | Mfg Equipment | 5 | Capitalized
EQP-100053 | Lithography System | Nikon NSR | Lithography System | Penang | APAC | Advantest | Automation Upgrade | EVT | P2 | Operational | Operational | 1850000 | 1750474 | -99526 | Dec 2025 | Feb 2026 | Mar 2026 | 46.4 | 25 | 40 | Medium | Automation | 7 | Capitalized
EQP-100054 | Automated Assembly | Kulicke & Soffa DB | Automated Assembly | Singapore | APAC | Teradyne | NPI Alpha | EVT | P4 | Operational | Operational | 650000 | 657988 | 7988 | Mar 2025 | May 2025 | Jul 2025 | 70.4 | 27 | 73 | Medium | Tooling | 5 | Capitalized
EQP-100055 | Vacuum System | Edwards STP | Vacuum System | Hsinchu, Taiwan | APAC | KLA Corporation | Automation Upgrade | EVT | P4 | Operational | Operational | 1850000 | 1978128 | 128128 | Feb 2025 | Apr 2025 | May 2025 | 62 | 42 | 54 | High | Mfg Equipment | 5 | Capitalized
EQP-100056 | CMP Tool | Lam Sabre | CMP Tool | Bangalore | APAC | Advantest | NPI Beta | DVT | P2 | OEM Build | OEM Build | 1280000 | 1262704 | -17296 | TBD | TBD | TBD | 88.5 | 25 | 93 | Low | Tooling | 5 | Not Started
EQP-100057 | Lithography System | ASML PAS | Lithography System | Santa Clara, CA | Americas | Hitachi High-Tech | Automation Upgrade | PVT | P4 | Installed | Installed | 1450000 | 1445962 | -4038 | Nov 2025 | TBD | TBD | 93.2 | 18 | 84 | Low | Automation | 7 | Not Started
EQP-100058 | Etch System | Lam Kiyo | Etch System | Austin, TX | Americas | Advantest | NPI Alpha | PVT | P1 | PO Issued | PO Issued | 820000 | 766671 | -53329 | TBD | TBD | TBD | 79.6 | 15 | 62 | Medium | Tooling | 7 | Not Started
EQP-100059 | Inspection System | Hitachi SEM | Inspection System | Hsinchu, Taiwan | APAC | Applied Materials | Tech Refresh | EVT | P2 | OEM Build | OEM Build | 1100000 | 1231433 | 131433 | TBD | TBD | TBD | 67.2 | 29 | 23 | Medium | Mfg Equipment | 5 | Not Started
EQP-100060 | Inspection System | KLA Puma | Inspection System | Bangalore | APAC | Hitachi High-Tech | Capacity Expansion | DVT | P1 | Installed | Installed | 1850000 | 1854459 | 4459 | Apr 2025 | TBD | TBD | 48.9 | 34 | 99 | Medium | Test Equipment | 5 | Not Started
EQP-100061 | Vacuum System | Leybold MAG | Vacuum System | Phoenix, AZ | Americas | Tokyo Electron | Automation Upgrade | PVT | P2 | Demand Identified | Demand Identified | 1100000 | 1158704 | 58704 | TBD | TBD | TBD | 52.9 | 38 | 11 | High | Automation | 5 | Not Started
EQP-100062 | Wafer Handling Robotics | RORZE RX | Wafer Handling Robotics | Bangalore | APAC | Advantest | Capacity Expansion | EVT | P4 | AIS Capitalized | AIS Capitalized | 1620000 | 1524955 | -95045 | Jul 2025 | Sep 2025 | Oct 2025 | 94.6 | 28 | 22 | Medium | Tooling | 5 | Capitalized
EQP-100063 | CMP Tool | AMAT Reflexion | CMP Tool | Guadalajara, MX | Americas | Applied Materials | Tech Refresh | PVT | P2 | Operational | Operational | 1100000 | 1182663 | 82663 | Jun 2025 | Aug 2025 | Sep 2025 | 76 | 18 | 100 | Low | Mfg Equipment | 5 | Capitalized
EQP-100064 | PECVD System | AMAT Producer | PECVD System | Hsinchu, Taiwan | APAC | Applied Materials | Tech Refresh | DVT | P3 | AIS Capitalized | AIS Capitalized | 650000 | 716251 | 66251 | Aug 2025 | Sep 2025 | Oct 2025 | 51.6 | 33 | 87 | Medium | Automation | 7 | Capitalized
EQP-100065 | Metrology Tool | KLA Zeta | Metrology Tool | Hsinchu, Taiwan | APAC | ASM International | Capacity Expansion | EVT | P2 | Delayed | Delayed | 650000 | 616298 | -33702 | TBD | TBD | TBD | 63.3 | 35 | 21 | High | Automation | 5 | Not Started
EQP-100066 | Automated Assembly | Kulicke & Soffa DB | Automated Assembly | Hsinchu, Taiwan | APAC | Hitachi High-Tech | Capacity Expansion | PVT | P2 | Operational | Operational | 1280000 | 1205336 | -74664 | Jan 2025 | Mar 2025 | May 2025 | 61.4 | 24 | 28 | Medium | Tooling | 5 | Capitalized
EQP-100067 | CMP Tool | Lam Sabre | CMP Tool | Ho Chi Minh City | APAC | Lam Research | NPI Beta | EVT | P4 | Operational | Operational | 1100000 | 1231104 | 131104 | May 2025 | Jul 2025 | Aug 2025 | 64.4 | 33 | 89 | Medium | Tooling | 5 | Capitalized
EQP-100068 | Test & Calibration | Xcerra Diamond | Test & Calibration | Phoenix, AZ | Americas | Teradyne | NPI Alpha | DVT | P3 | AIS Capitalized | AIS Capitalized | 1100000 | 1019197 | -80803 | Aug 2025 | Oct 2025 | Nov 2025 | 87.8 | 16 | 67 | Low | Automation | 5 | Capitalized
EQP-100069 | PECVD System | AMAT Producer | PECVD System | Bangalore | APAC | Tokyo Electron | NPI Alpha | DVT | P1 | Qualified | Qualified | 980000 | 1027374 | 47374 | Jan 2025 | Feb 2025 | TBD | 57.2 | 18 | 92 | Low | Test Equipment | 7 | In Progress
EQP-100070 | Etch System | AMAT Centris | Etch System | Shanghai | APAC | Tokyo Electron | NPI Beta | DVT | P3 | Demand Identified | Demand Identified | 2100000 | 1933190 | -166810 | TBD | TBD | TBD | 57.5 | 21 | 3 | Medium | Mfg Equipment | 7 | Not Started
EQP-100071 | Metrology Tool | KLA Surfscan | Metrology Tool | Penang | APAC | Tokyo Electron | Tech Refresh | DVT | P1 | OEM Build | OEM Build | 1100000 | 1023527 | -76473 | TBD | TBD | TBD | 68.8 | 33 | 85 | Medium | Mfg Equipment | 5 | Not Started
EQP-100072 | Vacuum System | Leybold MAG | Vacuum System | Shanghai | APAC | Applied Materials | Tech Refresh | DVT | P2 | AIS Capitalized | AIS Capitalized | 415000 | 386848 | -28152 | Jul 2025 | Sep 2025 | Oct 2025 | 69.5 | 38 | 29 | High | Mfg Equipment | 5 | Capitalized
EQP-100073 | Inspection System | Hitachi SEM | Inspection System | Phoenix, AZ | Americas | Lam Research | NPI Beta | DVT | P3 | AIS Capitalized | AIS Capitalized | 2100000 | 2162309 | 62309 | Nov 2025 | Jan 2026 | Feb 2026 | 67.7 | 37 | 32 | High | Mfg Equipment | 5 | Capitalized
EQP-100074 | Automated Assembly | Besi Esec | Automated Assembly | Shanghai | APAC | Teradyne | Automation Upgrade | EVT | P2 | OEM Build | OEM Build | 1620000 | 1619588 | -412 | TBD | TBD | TBD | 78.3 | 33 | 39 | Medium | Tooling | 5 | Not Started
EQP-100075 | Etch System | Lam Flex | Etch System | Austin, TX | Americas | Lam Research | Automation Upgrade | EVT | P3 | Qualified | Qualified | 1280000 | 1385412 | 105412 | Oct 2025 | Jan 2026 | TBD | 61.5 | 17 | 72 | Low | Automation | 7 | In Progress
EQP-100076 | Wafer Handling Robotics | RORZE RX | Wafer Handling Robotics | Santa Clara, CA | Americas | ASM International | Tech Refresh | DVT | P2 | Operational | Operational | 2100000 | 2145113 | 45113 | Sep 2025 | Oct 2025 | Nov 2025 | 62.5 | 33 | 34 | Medium | Automation | 5 | Capitalized
EQP-100077 | Test & Calibration | Teradyne UltraFLEX | Test & Calibration | Ho Chi Minh City | APAC | Applied Materials | Tech Refresh | PVT | P3 | Operational | Operational | 1100000 | 1018369 | -81631 | Jun 2025 | Aug 2025 | Sep 2025 | 45.3 | 19 | 92 | Low | Tooling | 5 | Capitalized
EQP-100078 | Etch System | Lam Flex | Etch System | Santa Clara, CA | Americas | Lam Research | Tech Refresh | EVT | P2 | AIS Capitalized | AIS Capitalized | 1620000 | 1600850 | -19150 | Jun 2025 | Aug 2025 | Oct 2025 | 49.2 | 13 | 39 | Medium | Test Equipment | 7 | Capitalized
EQP-100079 | Test & Calibration | Teradyne UltraFLEX | Test & Calibration | Austin, TX | Americas | ASM International | Automation Upgrade | PVT | P2 | Operational | Operational | 2100000 | 2117658 | 17658 | Sep 2025 | Nov 2025 | Dec 2025 | 66.5 | 28 | 95 | Medium | Tooling | 5 | Capitalized
EQP-100080 | Automated Assembly | Besi Esec | Automated Assembly | Bangalore | APAC | Applied Materials | NPI Beta | DVT | P4 | AIS Capitalized | AIS Capitalized | 415000 | 382438 | -32562 | Apr 2025 | Jun 2025 | Jul 2025 | 59.5 | 17 | 20 | Medium | Tooling | 5 | Capitalized
EQP-100081 | Wafer Handling Robotics | Brooks Reliance | Wafer Handling Robotics | Phoenix, AZ | Americas | Teradyne | Tech Refresh | PVT | P2 | PO Issued | PO Issued | 1850000 | 2010341 | 160341 | TBD | TBD | TBD | 66.8 | 39 | 29 | High | Automation | 5 | Not Started
EQP-100082 | Test & Calibration | Advantest T2000 | Test & Calibration | Guadalajara, MX | Americas | Teradyne | Automation Upgrade | DVT | P1 | Operational | Operational | 415000 | 461994 | 46994 | Nov 2025 | Jan 2026 | Feb 2026 | 49.4 | 16 | 51 | Medium | Tooling | 5 | Capitalized
EQP-100083 | Test & Calibration | Advantest T2000 | Test & Calibration | Singapore | APAC | Lam Research | Automation Upgrade | DVT | P3 | Operational | Operational | 980000 | 966881 | -13119 | Sep 2025 | Oct 2025 | Dec 2025 | 70.5 | 32 | 64 | Medium | Test Equipment | 5 | Capitalized
EQP-100084 | Lithography System | TEL Lithius | Lithography System | Phoenix, AZ | Americas | ASM International | NPI Beta | EVT | P3 | OEM Build | OEM Build | 650000 | 621028 | -28972 | TBD | TBD | TBD | 83 | 38 | 92 | High | Automation | 7 | Not Started
EQP-100085 | Inspection System | KLA Puma | Inspection System | Hsinchu, Taiwan | APAC | Lam Research | Automation Upgrade | DVT | P3 | AIS Capitalized | AIS Capitalized | 1100000 | 1142112 | 42112 | Feb 2025 | Apr 2025 | May 2025 | 67.6 | 13 | 67 | Low | Automation | 5 | Capitalized
EQP-100086 | Etch System | AMAT Centris | Etch System | Austin, TX | Americas | Teradyne | Automation Upgrade | PVT | P3 | PO Issued | PO Issued | 415000 | 419127 | 4127 | TBD | TBD | TBD | 75.3 | 42 | 39 | High | Mfg Equipment | 7 | Not Started
EQP-100087 | Vacuum System | Edwards STP | Vacuum System | Penang | APAC | Lam Research | Tech Refresh | PVT | P1 | Delayed | Delayed | 980000 | 1040293 | 60293 | TBD | TBD | TBD | 52.9 | 33 | 56 | High | Tooling | 5 | Not Started
EQP-100088 | Wafer Handling Robotics | Entegris Probot | Wafer Handling Robotics | Guadalajara, MX | Americas | Applied Materials | Capacity Expansion | EVT | P2 | Operational | Operational | 1850000 | 1953000 | 103000 | Dec 2025 | Feb 2026 | Mar 2026 | 61.7 | 19 | 64 | Medium | Automation | 5 | Capitalized
EQP-100089 | Wafer Handling Robotics | Brooks Reliance | Wafer Handling Robotics | Guadalajara, MX | Americas | Lam Research | Capacity Expansion | PVT | P2 | Installed | Installed | 1280000 | 1385775 | 105775 | Dec 2025 | TBD | TBD | 77.3 | 37 | 85 | High | Automation | 5 | Not Started
EQP-100090 | PECVD System | AMAT Producer | PECVD System | Bangalore | APAC | KLA Corporation | NPI Beta | DVT | P4 | Delayed | Delayed | 1620000 | 1552609 | -67391 | TBD | TBD | TBD | 87.2 | 16 | 84 | High | Mfg Equipment | 7 | Not Started
EQP-100091 | Inspection System | Hitachi SEM | Inspection System | Phoenix, AZ | Americas | Teradyne | NPI Beta | EVT | P1 | Operational | Operational | 2100000 | 2271798 | 171798 | Aug 2025 | Sep 2025 | Nov 2025 | 63.2 | 25 | 76 | Low | Automation | 5 | Capitalized
EQP-100092 | Vacuum System | Edwards STP | Vacuum System | Singapore | APAC | Tokyo Electron | Capacity Expansion | DVT | P4 | Delayed | Delayed | 980000 | 973696 | -6304 | TBD | TBD | TBD | 83.9 | 42 | 87 | High | Tooling | 5 | Not Started
EQP-100093 | Metrology Tool | KLA Surfscan | Metrology Tool | Guadalajara, MX | Americas | KLA Corporation | Capacity Expansion | EVT | P3 | Operational | Operational | 1280000 | 1319562 | 39562 | Sep 2025 | Nov 2025 | Dec 2025 | 49.2 | 20 | 54 | Medium | Tooling | 5 | Capitalized
EQP-100094 | Automated Assembly | Kulicke & Soffa DB | Automated Assembly | Ho Chi Minh City | APAC | Lam Research | NPI Beta | DVT | P4 | AIS Capitalized | AIS Capitalized | 415000 | 416236 | 1236 | Jul 2025 | Aug 2025 | Oct 2025 | 94.7 | 33 | 48 | Medium | Mfg Equipment | 5 | Capitalized
EQP-100095 | Inspection System | KLA Puma | Inspection System | Penang | APAC | KLA Corporation | NPI Beta | EVT | P2 | Operational | Operational | 1620000 | 1715927 | 95927 | Dec 2025 | Mar 2026 | Apr 2026 | 75.8 | 15 | 22 | Medium | Automation | 5 | Capitalized
EQP-100096 | Lithography System | TEL Lithius | Lithography System | Singapore | APAC | Teradyne | NPI Alpha | DVT | P2 | AIS Capitalized | AIS Capitalized | 650000 | 604207 | -45793 | Nov 2025 | Jan 2026 | Feb 2026 | 50.5 | 41 | 96 | High | Mfg Equipment | 7 | Capitalized
EQP-100097 | Automated Assembly | Besi Esec | Automated Assembly | Shanghai | APAC | KLA Corporation | Capacity Expansion | DVT | P1 | AIS Capitalized | AIS Capitalized | 1280000 | 1239184 | -40816 | Dec 2025 | Jan 2026 | Mar 2026 | 93.7 | 14 | 87 | Low | Mfg Equipment | 5 | Capitalized
EQP-100098 | Wafer Handling Robotics | Entegris Probot | Wafer Handling Robotics | Santa Clara, CA | Americas | Teradyne | Capacity Expansion | DVT | P3 | AIS Capitalized | AIS Capitalized | 1280000 | 1379461 | 99461 | Dec 2025 | Jan 2026 | Mar 2026 | 81.8 | 31 | 37 | Medium | Mfg Equipment | 5 | Capitalized
EQP-100099 | Inspection System | Hitachi SEM | Inspection System | Penang | APAC | KLA Corporation | Automation Upgrade | PVT | P2 | Operational | Operational | 820000 | 887485 | 67485 | Aug 2025 | Oct 2025 | Nov 2025 | 55.1 | 22 | 25 | Medium | Automation | 5 | Capitalized
EQP-100100 | CMP Tool | Lam Sabre | CMP Tool | Ho Chi Minh City | APAC | Advantest | Capacity Expansion | EVT | P3 | Demand Identified | Demand Identified | 980000 | 957677 | -22323 | TBD | TBD | TBD | 51.2 | 33 | 13 | Medium | Tooling | 5 | Not Started
EQP-100101 | Vacuum System | Pfeiffer HiPace | Vacuum System | Penang | APAC | KLA Corporation | Automation Upgrade | PVT | P2 | Operational | Operational | 1850000 | 1800686 | -49314 | Aug 2025 | Sep 2025 | Nov 2025 | 75.1 | 21 | 89 | Low | Automation | 5 | Capitalized
EQP-100102 | Inspection System | KLA Puma | Inspection System | Austin, TX | Americas | Hitachi High-Tech | Capacity Expansion | DVT | P2 | AIS Capitalized | AIS Capitalized | 1450000 | 1382326 | -67674 | Aug 2025 | Sep 2025 | Nov 2025 | 75.7 | 37 | 55 | High | Mfg Equipment | 5 | Capitalized
EQP-100103 | Etch System | AMAT Centris | Etch System | Ho Chi Minh City | APAC | Hitachi High-Tech | Tech Refresh | PVT | P3 | Installed | Installed | 415000 | 393650 | -21350 | Aug 2025 | TBD | TBD | 48.4 | 33 | 66 | Medium | Tooling | 7 | Not Started
EQP-100104 | Test & Calibration | Teradyne UltraFLEX | Test & Calibration | Guadalajara, MX | Americas | KLA Corporation | Automation Upgrade | DVT | P2 | Qualified | Qualified | 650000 | 672609 | 22609 | Jul 2025 | Sep 2025 | TBD | 57.5 | 17 | 23 | Medium | Test Equipment | 5 | In Progress
EQP-100105 | Vacuum System | Leybold MAG | Vacuum System | Ho Chi Minh City | APAC | Lam Research | Capacity Expansion | DVT | P3 | Operational | Operational | 980000 | 1096887 | 116887 | Sep 2025 | Oct 2025 | Nov 2025 | 51.8 | 14 | 77 | Low | Test Equipment | 5 | Capitalized
EQP-100106 | Vacuum System | Edwards STP | Vacuum System | Penang | APAC | Hitachi High-Tech | NPI Alpha | PVT | P2 | OEM Build | OEM Build | 1100000 | 1199299 | 99299 | TBD | TBD | TBD | 70.4 | 17 | 45 | Medium | Test Equipment | 5 | Not Started
EQP-100107 | Lithography System | ASML PAS | Lithography System | Santa Clara, CA | Americas | Hitachi High-Tech | Tech Refresh | PVT | P2 | Demand Identified | Demand Identified | 1850000 | 1750015 | -99985 | TBD | TBD | TBD | 95 | 40 | 16 | High | Tooling | 7 | Not Started
EQP-100108 | Wafer Handling Robotics | RORZE RX | Wafer Handling Robotics | Austin, TX | Americas | KLA Corporation | Capacity Expansion | PVT | P1 | AIS Capitalized | AIS Capitalized | 1620000 | 1710755 | 90755 | Oct 2025 | Dec 2025 | Jan 2026 | 83.4 | 18 | 75 | Low | Mfg Equipment | 5 | Capitalized
EQP-100109 | Etch System | AMAT Centris | Etch System | Phoenix, AZ | Americas | ASM International | NPI Beta | EVT | P2 | Delayed | Delayed | 980000 | 969420 | -10580 | TBD | TBD | TBD | 54.8 | 27 | 36 | High | Automation | 7 | Not Started
EQP-100110 | Test & Calibration | Xcerra Diamond | Test & Calibration | Austin, TX | Americas | KLA Corporation | Tech Refresh | PVT | P1 | Installed | Installed | 2100000 | 2234665 | 134665 | Oct 2025 | TBD | TBD | 49.1 | 26 | 46 | High | Tooling | 5 | Not Started